## Sheet1
| Phase | Beginn | Ausarbeitung | Konstruktion | Umsetzung
| Artefakt | Inception | Elaboration | Construction | Transition
Arbeitsschritt | Iteration: | I1 | E1..En | C1..cn | T1..Tn
Business Modeling | Domain Model |  | s
Requirements | Use-Case-Model | s | r
| Vision | s | r
| Supplementary Specification | s | r
| Glossary | s | r
Design | Design Model |  | s | r
| SW Architecture Document |  | s
| Data Model |  | s | r
Implementation | Implementation Model |  | s | r | r
Project Management | SW Development Plan | s | r | r | r
Testing | Test Model |  | s | r
Enviroment | Development Case | s | r
s - start; r - refine